## Cover
MicroStrategy Cloud Migration Roles, Responsibilities & RACI Matrix
On-Prem → CMC Cluster ¦ Version 3.0 ¦ April 2026 ¦ Confidential
HCL MIGRATION TEAM
Primary delivery team. Executes all technical migration work end-to-end — discovery scripts, package migration, user/DB migration, cache warm-up, validation, and hypercare. Includes a dedicated MSTR admin to support EBI.
EBI TEAM (Internal Core Admin & Coordinator)
Owns the MSTR platform internally. Raises and tracks all ACL/access requests. Acts as the bridge between HCL, Business, and post-migration SRE. Provides MSTR admin support and ensures smooth coordination throughout.
BUSINESS TEAM
Accountable for business sign-off. Validates critical reports during UAT. Minimal manual effort by design — automated tooling handles discovery and validation; business touch points are kept to review gates only.
SRE TEAM ⚠ Post-Migration Only
NOT involved during migration phases. Engages after CMC go-live. Owns platform reliability, GKE secrets management, monitoring, alerting, and long-term runbook stewardship on the cloud platform.
RACI LEGEND
R — Responsible | Does the work / executes the task
A — Accountable | Owns the outcome; ultimate decision-maker
C — Consulted | Input required before task is completed
I — Informed | Kept updated; no action required
(blank) — N/A | Not involved in this task
WORKBOOK CONTENTS
1. Cover | This page — team descriptions and legend
2. Team Profiles | All roles, responsibilities, skills, and FTEs per team
3. RACI Matrix | Full task-level ownership matrix (all 4 teams, 50+ tasks)
4. Phase Task Plan | Detailed per-phase tasks with acceptance criteria
5. Effort Summary | Estimated hours per team per phase with manual comparison

## Team Profiles
HCL MIGRATION TEAM — Primary Technical Delivery
Role / Title | Key Responsibilities | Required Skills & Tools | FTEs | Phase Focus | Notes
HCL Project Manager | Single point of accountability for HCL delivery. Manages scope, schedule, risks, and issues. Runs daily stand-ups. Produces weekly status report. Owns go/no-go gate presentation. | PMP / Prince2, MSTR delivery experience, CMC programme management, RAID log management | 1 | All phases | Escalation path: EBI Project Coordinator → Business Sponsor
HCL Lead MSTR Migration Engineer | Architects the end-to-end migration approach. Executes package export/import via mstr_package_migrator.py. Resolves package conflicts. Verifies object counts. Owns migration runbook. | MSTR architecture, REST API v2, Command Manager, .mmp package conflicts, MSTR 2021+ | 1 | Phase 2 primary | Runs: mstr_package_migrator.py, mstr_command_manager.scp
HCL MSTR Admin | Supports EBI MSTR admin on all platform admin tasks. Runs harvest scripts. Configures VLDB properties, schedules, and security filters via Command Manager. Supports post-import verification. | MSTR admin, MSTR Workstation, Developer, Command Manager, VLDB settings | 1 | Phase 1 + Phase 2 | Runs: mstr_harvester.py, extended_command_manager.scp
HCL Discovery & Validation Engineer | Executes Phase 1 harvest and Phase 3 validation end-to-end. Feeds reports to AI. Reviews DIFF_REPORT.csv. Triages CRITICAL/HIGH items. Prepares sign-off evidence package. | Python 3, MSTR REST API, diff analysis, Excel/CSV review, AI prompting | 1 | Phase 1 + Phase 3 | Runs: mstr_harvester.py, mstr_validator.py, full_validation_runner.py
HCL DB & Connectivity Engineer | Manages all database connection work. Runs mstr_connectivity_tester.py and mstr_db_connection_creator.py. Resolves JDBC errors (SingleStore, SQL Server, Oracle). Validates IS-side connectivity. | JDBC, ODBC, odbc.ini parsing, SQL Server, SingleStore, Oracle, TCP/SSL debugging | 1 | Phase 1 + Phase 2 | Runs: mstr_connectivity_tester.py, mstr_db_connection_creator.py
HCL User & Security Migration Engineer | Executes bulk user, group, and membership migration. Assigns security filters. Recreates LDAP/SAML config. Handles Standard/LDAP/SAML account types correctly. | MSTR user management, LDAP, SAML, REST API, mstr_user_migrator.py, security filters | 1 | Phase 2 | Runs: mstr_user_migrator.py, extended_command_manager.scp security filter sections
EBI TEAM — Internal Core Admin, ACL Management & Coordination
Role / Title | Key Responsibilities | Required Skills & Tools | FTEs | Phase Focus | Notes
EBI Project Coordinator | Primary liaison between HCL, Business, and SRE. Chairs weekly steering meetings. Owns the issues and actions log. Escalates blockers. Ensures all teams have what they need at each gate. Coordinates sign-off communications. | Project coordination, stakeholder management, MSTR programme familiarity, RAID log | 1 | All phases | Acts as the connective tissue across all teams
EBI MSTR Platform Admin | Internal MSTR admin authority. Provides IS admin credentials to HCL securely. Validates migrated objects against internal catalogues. Owns MSTR platform config decisions (project names, VLDB standards). Reviews all admin changes before apply. | MSTR admin (Developer + Workstation + Web Admin), MicroStrategy Cloud admin portal, LDAP integration | 1 | All phases | Final word on any MSTR platform configuration decision
EBI ACL & Access Management Specialist | Raises and tracks ALL access and permission requests throughout migration. Manages: IS admin credentials, DB firewall rules, LDAP/AD service account permissions, CMC admin portal access. Maintains access log. Reviews post-migration access vs. least-privilege policy. | IAM, Active Directory, firewall rule management, GCP IAM, change management, access governance | 1 | All phases | No access change proceeds without an approved ACL request through this role
EBI Change Management & Communications Lead | Manages change communications to end users and stakeholders. Drafts go-live communications. Coordinates training sessions. Maintains change log. Ensures business readiness before cutover. | Change management (PROSCI/ADKAR), internal communications, MSTR end-user knowledge | 1 | Phase 2 + Phase 3 | Owns all stakeholder-facing communications
BUSINESS TEAM — Validation Sign-Off (Minimum Manual Effort)
Role / Title | Key Responsibilities | Required Skills & Tools | FTEs | Phase Focus | Notes
Business Sponsor | Provides final go/no-go authority for CMC cutover. Reviews AI-generated sign-off report. Signs off on UAT completion. Represents business interests at all major decision gates. Escalation point for business-blocking issues. | Executive stakeholder, MSTR usage awareness, budget authority | 1 | Phase 3 gates + Post-migration | Involved at gate reviews only — not in day-to-day migration
Business Analyst / Power User | Performs targeted UAT on 5–10 priority business-critical reports. Confirms data accuracy against known on-prem outputs. Reviews DIFF_REPORT summary. Provides formal UAT sign-off. Participates in post-migration performance review. | MSTR report authoring and consumption, data domain knowledge, UAT documentation | 1–2 | Phase 3 UAT | Automated tools handle discovery; BA focuses only on business-critical UAT
Report Owner / Subject Matter Expert (SME) | Identifies which reports are business-critical for UAT prioritisation. Validates specific data outputs that require domain knowledge. Signs off on individual report accuracy during UAT. | Domain expertise (Finance/Sales/Operations), MSTR Web user | 2–3 | Phase 3 UAT | Engaged only for specific report sign-off — not for technical tasks
SRE TEAM ⚠ POST-MIGRATION ONLY — Platform Reliability & Security
⚠ SRE team is NOT involved during Phases 1, 2, or 3 of the migration. They are engaged ONLY after the CMC go-live cutover is confirmed and hypercare handover is initiated.
Role / Title | Key Responsibilities | Required Skills & Tools | FTEs | Phase Focus | Notes
SRE Lead | Accepts handover from HCL after hypercare. Owns production runbook. Defines and monitors SLOs for CMC IS (availability, latency, error rate). Incident commander for P1/P2 issues post go-live. | SRE practices, GKE, SLO definition, incident management, MSTR IS ops | 1 | Post-migration | Handover pack from HCL required before SRE Lead engages
Platform & GKE Engineer | Provisions GKE namespaces and MSTR pod resources. Installs External Secrets Operator. Wires Workload Identity to Google Secret Manager. Configures Gatekeeper constraint exceptions for MSTR namespace. Manages ongoing K8s infrastructure. | GKE, Kubernetes, Helm, Workload Identity, ESO, OPA Gatekeeper | 1–2 | Post-migration | Responsible for the secrets-management architecture raised by EBI ACL Specialist
Security Engineer | Implements long-term secrets management (GSM + ESO or Vault). Reviews Gatekeeper policies for MSTR namespace. Audits pod specs for plaintext credentials. Reviews LDAP/SAML configuration on CMC IS. | GCP Security, OPA Gatekeeper, Secret Manager, HashiCorp Vault, LDAP/SAML | 1 | Post-migration | Picks up security items surfaced by EBI ACL Specialist during migration
Observability Engineer | Deploys Prometheus/Grafana or GCP Cloud Ops for CMC IS monitoring. Sets alert thresholds for IS health, cache hit rates, report failure rates. Creates on-call runbook and escalation matrix. | Prometheus, Grafana, GCP Cloud Ops, alerting, MSTR health metrics | 1 | Post-migration | Monitoring must be live before SRE Lead accepts production handover

## RACI Matrix
RACI: R = Responsible (does work) A = Accountable (owns outcome) C = Consulted (input needed) I = Informed (kept updated) ⚠ SRE columns apply to POST-MIGRATION only
⚠ SRE — POST-MIGRATION ONLY
Task / Activity | HCL MIGRATION TEAM | [5 empty] | EBI TEAM |  |  |  | BUSINESS TEAM |  |  | SRE TEAM (Post-Migration)
| HCL PM | HCL Lead Engr | HCL MSTR Adm | HCL Disc/Val | HCL DB Engr | HCL User Engr | EBI Coord | EBI MSTR Adm | EBI ACL | EBI Change | Biz Sponsor | BA / Power Usr | Report SME | SRE Lead | SRE Platform | SRE Security | SRE Observ.
| HCL Project Mgr | HCL Lead Migration Engr | HCL MSTR Admin | HCL Discovery & Validation Engr | HCL DB & Connectivity Engr | HCL User & Security Engr | EBI Project Coordinator | EBI MSTR Platform Admin | EBI ACL & Access Specialist | EBI Change Mgmt Lead | Business Sponsor | Business BA / Power User | Business Report SME | SRE Lead (Post only) | SRE Platform Engr (Post only) | SRE Security Engr (Post only) | SRE Observability (Post only)
PHASE 1 — DISCOVERY
1.01 Obtain IS admin credentials & access request | I | I | I | I | I | I | A | C | R | I | I
1.02 Confirm HTTPS/443 access from admin laptop to on-prem IS | I | C | C | C | R |  | I | C | A
1.03 Run mstr_harvester.py — full metadata harvest (all projects) | I | C | C | A/R | C |  | I | C
1.04 Review SUMMARY_REPORT.txt — risk flags & object counts | C | C | C | A/R |  |  | C | C |  |  | I | C
1.05 AI risk analysis — feed SUMMARY_REPORT.txt, produce risk matrix | I: A; I: C; I: R; A: C; C: C; I: I | C
1.06 Run mstr_connectivity_tester.py — all odbc.ini DSNs | I | C |  | C | A/R |  | I | C | I
1.07 Raise firewall/ACL request for DB hosts not reachable from CMC | I: I; I: I; I: C; I: C; A: C; R: A/R
1.08 Document LDAP/SAML/SMTP configuration for cloud re-entry | I | C | A | C |  |  | I | R | C
1.09 User inventory analysis — identify stale / over-privileged accounts | I | C |  | A/R |  | C | C | C |  |  | C | C
1.10 Business review of user deactivation list — approvals | I |  |  | C |  | C | A | C |  | C | R | C
1.11 Security filter inventory — confirm all filters documented | I | C | C | A/R |  |  | C | R | C |  | C
1.12 Schedule & subscription audit — review counts vs on-prem | I | C | C | A/R |  |  | C | C |  |  | I | C
1.13 Raise CMC IS admin access ACL request | I: I; I: I; A: C; C: C; R: A/R; I: I
1.14 Produce Phase 1 Discovery Report deliverable | A | C |  | R | C |  | C | C |  |  | I
1.15 Phase 1 sign-off and migration go/no-go brief | I: A/R; I: C; I: C; A: C; C: C; I: R
PHASE 2 — MIGRATION EXECUTION
2.01 CMC IS pre-flight — confirm reachability, credentials, port 34952 | I | C | C | C | C |  | I | A | R
2.02 Raise ACL request for CMC IS admin portal access | I: I; A: C; C: C; R: A/R; I: I
2.03 Run mstr_package_migrator.py — export packages from on-prem | I: I; I: A/R; I: C; I: C; A: I; C: C
2.04 Resolve package pre-export conflicts / missing dependencies | I: C; I: A/R; I: C; I: C; A: I; C: C
2.05 Run mstr_package_migrator.py — import packages to cloud IS | I: I; I: A/R; I: C; I: C; A: I; C: C
2.06 Resolve package import conflicts / object ACL errors | C | A/R | C | C |  |  | C | C | R
2.07 Verify object counts post-import vs 09_reports.csv baseline | I: I; I: C; I: C; I: A/R; A: I; C: R
2.08 Run mstr_user_migrator.py — bulk-create users/groups/memberships | I | C | C |  |  | A/R | I | C | I
2.09 Review migrated user list — confirm accuracy vs 03_users.csv | I | C | C | C |  | C | C | A |  |  | C
2.10 Assign security filters — extended_command_manager.scp | I | C | C |  |  | A/R | I | C | C |  | C
2.11 Run mstr_db_connection_creator.py — create all datasources from odbc.ini | I: I; I: C; I: A/R; A: I; C: C
2.12 Run IS-side testConnection for each datasource | I: I; I: C; I: A/R; A: I; C: C; R: I
2.13 Resolve JDBC errors — SingleStore (driver JAR, URL, SSL, auth plugin) | I: I; I: C; I: A/R; A: I; C: C; R: C
2.14 Resolve JDBC errors — SQL Server / Oracle / other DBs | I: I; I: C; I: A/R; A: I; C: C; R: C
2.15 Raise firewall/ACL for DB hosts unreachable from cloud IS | I: I; I: I; I: C; A: C; C: C; R: A/R
2.16 Fix free-form SQL string→date auto-conversion (CAST / VLDB) | I | C | A/R | C | C |  | I | C
2.17 Bulk VLDB property changes (project-level) — extended_command_manager.scp | I: I; I: C; I: A/R; I: C; A: I; C: R
2.18 Recreate schedules on cloud IS — extended_command_manager.scp | I | C | A/R | C |  |  | I | C |  |  | C
2.19 Confirm schedule requirements with business before recreating | I: I; I: C; A: A; C: C; I: C; I: C | R
2.20 Re-enter LDAP/SAML config on cloud IS | I | C | A | C |  | R | I | R | C
2.21 Raise ACL request for LDAP/AD service account on cloud IS | I: I; I: C; A: C; C: C; R: A/R
2.22 Re-enter SMTP/email config on cloud IS | I: I; I: C; I: A; I: C; A: I; C: R
2.23 Run mstr_cache_warmer.py — pre-warm top-50 reports before go-live | I: I; I: C; I: C; I: A/R; A: I; C: C
2.24 Weekly migration status report to all stakeholders | I: A/R; A: C; I: C; I: I
2.25 Phase 2 completion sign-off — confirm cloud IS ready for validation | A/R | C | C | C | C | C | R | C |  |  | I
PHASE 3 — VALIDATION & SIGN-OFF
3.01 Re-harvest cloud IS — run mstr_harvester.py on cloud | I: I; I: C; I: C; I: A/R; A: I; C: C
3.02 Run full_validation_runner.py — automated diff vs on-prem baseline | I: I; I: C; I: A/R; I: C; A: I; C: C
3.03 Review DIFF_REPORT.csv — CRITICAL severity items | C | C | C | A/R | C | C | C | C |  |  | I
3.04 Review DIFF_REPORT.csv — HIGH severity items | C | C | C | A/R | C | C | C | C |  |  | I | C
3.05 Fix CRITICAL defects — missing objects / broken connections | C | A/R | C | C | R | C | I | C | C
3.06 Fix HIGH defects — schedule gaps, user discrepancies | C | A/R | C | C |  | C | I | C | C
3.07 Re-run validation after all fixes — confirm CRITICAL count = 0 | I | C |  | A/R | C |  | I | C
3.08 IS-side DB connectivity re-test for all fixed connections | I | C |  | C | A/R |  | I | C | I
3.09 Identify priority reports for business UAT (top 5–10) | C: I; C: C; I: A; C: C |  | C | R | C
3.10 Business UAT — execute priority reports on cloud IS | [9 empty] | C | I | A/R | R | bar: C to C
3.11 Log and prioritise UAT defects | C: I; A/R: C; C: C; I: A; C: C | C | I | C | R
3.12 Resolve UAT defects raised by business | C | A/R | C | C | C | C | I | C | C |  | I | I
3.13 Generate AI sign-off report — feed VALIDATION_REPORT.txt | C: C; C: A/R; I: C; C: C |  | I
3.14 Business review of AI sign-off report | [9 empty] | A | R | C | bar: C to C
3.15 Prepare cutover communication to end users | [9 empty] | A/R | C | C | bar: C; I
3.16 Final go/no-go gate — all parties confirm readiness | C | C | C | C | C | C | A/R | C |  | C | R
3.17 CMC go-live cutover — flip DNS / redirect users to cloud IS | R | C | C |  |  |  | A | C | C | C | I
POST-MIGRATION & HYPERCARE (SRE team now engages)
4.01 Week 1 hypercare — HCL on-call, P1 response ≤ 2 hrs | A | R | R | R | R | R | C | C |  |  | I |  |  | I
4.02 Monitor IS health — cache hit rates, report failures, query times | [13 empty] | A | R |  | R | bar: C to C
4.03 GKE namespace, secrets (GSM + ESO), Workload Identity setup | [13 empty] | C | A/R | R | bar: C; I; C
4.04 Gatekeeper policy exception + secrets audit (no plaintext) | [13 empty] | C | C | A/R | bar: C to C
4.05 Deploy monitoring dashboards & alerting (Prometheus/Cloud Ops) | [13 empty] | C | C |  | A/R | bar: I
4.06 Handover — runbooks, scripts, and access transferred to EBI + SRE | A/R | R | R | R | R | R | C | C |  |  | I |  |  | C | C | C | C
4.07 Post-migration performance review (30-day SLO report) | [9 empty] | C | R | C |  | A | C |  | C | bar: C to A/R; I to C
4.08 User communication + training on CMC differences | [9 empty] | A/R | R | C | C | bar: C to C
4.09 Project close-out — lessons learned, final status report | C: A/R; A/R: C; C: C; I: R; C: C | C | C |  |  | I

## Phase Task Plan
# | Task / Deliverable | HCL Responsibility | EBI Responsibility | Business Responsibility | Script / Tool | Acceptance Criteria
PHASE 1 — DISCOVERY
1.01 | Obtain IS admin credentials & access | Request credentials via EBI ACL process; confirm laptop → IS HTTPS connectivity | Raise access request; provision admin credentials securely to HCL PM | Provide IS URL and confirm access window | — | HCL engineer can authenticate to IS REST API
1.02 | Run mstr_harvester.py — full metadata harvest | Execute with --all-projects flag; verify 21 CSV files and SUMMARY_REPORT.txt generated | MSTR Admin reviews output file list; confirms no critical objects missed | — | mstr_harvester.py | 21 CSVs + SUMMARY_REPORT.txt present; no Python exceptions in log
1.03 | AI risk analysis from SUMMARY_REPORT.txt | Feed to Claude/ChatGPT; produce ranked risk matrix and migration order | Review risk matrix; flag any internal concerns or restrictions | Business Sponsor reviews top-3 CRITICAL risks and confirms awareness | Claude / ChatGPT | Signed risk matrix on record; migration order agreed
1.04 | DB connectivity test — all odbc.ini DSNs | Run mstr_connectivity_tester.py; review UNREACHABLE results | ACL Specialist raises firewall requests for any UNREACHABLE host:port | — | mstr_connectivity_tester.py | connectivity_results.csv complete; all UNREACHABLE items have ACL request raised
1.05 | User inventory analysis & deactivation approval | Feed 03_users.csv to AI; produce stale/over-privileged user list | EBI Coordinator circulates deactivation list for business approval | Business Sponsor approves deactivation list within 2 business days | mstr_harvester.py output | Approved deactivation list signed by Business Sponsor
1.06 | Security filter, schedule & subscription audit | Review 07_security_filters.csv, 16_schedules.csv, 17_subscriptions.csv | MSTR Admin validates counts match internal records | BA confirms subscription list is current and recipients correct | mstr_harvester.py output | Any discrepancy logged as a known issue before Phase 2 begins
1.07 | Phase 1 sign-off and go/no-go decision | Produce Phase 1 Discovery Report; present to EBI Coordinator | EBI Coordinator chairs go/no-go meeting; confirms all gates passed | Business Sponsor provides written approval to proceed to Phase 2 | — | Signed go/no-go record; Phase 2 start date confirmed
PHASE 2 — MIGRATION EXECUTION
2.01 | CMC cluster pre-flight & credential setup | Confirm IS port 34952 reachable; run test REST API call | MSTR Admin confirms CMC IS admin portal access; ACL Specialist provisions creds | — | mstr_harvester.py (smoke test) | REST API /status returns HTTP 200 on cloud IS
2.02 | Project package export from on-prem IS | Run mstr_package_migrator.py --mode export-only per project; store .mmp files | MSTR Admin reviews exported package manifest; confirms all projects captured | — | mstr_package_migrator.py | .mmp files present for each project; no export errors in log
2.03 | Project package import to cloud IS | Run mstr_package_migrator.py --mode import-only; monitor import job status | MSTR Admin monitors cloud IS during import; approves object conflict resolutions | — | mstr_package_migrator.py | All projects loaded; import status = COMPLETED; object counts within 1% of baseline
2.04 | User, group & membership migration | Run mstr_user_migrator.py --mode full from discovery CSVs | MSTR Admin reviews user_migration_results.csv; confirms built-ins skipped | BA confirms user count and group structure matches expectations | mstr_user_migrator.py | User count ≥ 99% of baseline; all groups present; memberships verified
2.05 | Security filter assignment | Run extended_command_manager.scp Section 5 (bulk security filter assign) | MSTR Admin verifies filter assignments on cloud IS via MSTR Workstation | Report SME spot-checks data visibility on 3 key accounts | extended_command_manager.scp | Zero security filter assignment errors; data governance intact
2.06 | DB connections: create on cloud IS + IS-side connectivity test | Run mstr_db_connection_creator.py --mode create-and-test | ACL Specialist raises firewall rules for UNREACHABLE results | — | mstr_db_connection_creator.py | All connections REACHABLE or REACHABLE_AUTH_NEEDED; no UNREACHABLE without ACL in progress
2.07 | Resolve JDBC errors (SingleStore, SQL Server, others) | Fix JAR, JDBC URL, SSL mode, auth plugin per troubleshooting guide | ACL Specialist raises any network-level ACL needed; MSTR Admin re-tests | — | mstr_db_connection_creator.py | testConnection returns success or REACHABLE_AUTH_NEEDED for all DSNs
2.08 | VLDB, schedules, LDAP/SAML, SMTP re-configuration | Run extended_command_manager.scp Sections 1-3, 10-11 | MSTR Admin verifies all settings on cloud IS match on-prem baseline | BA confirms schedule timings match business requirements | extended_command_manager.scp | All enabled schedules recreated; VLDB properties verified; LDAP/SAML test login passes
2.09 | Cache warm-up — pre-warm top-50 reports | Run mstr_cache_warmer.py --top-n 50 before go-live window | MSTR Admin monitors IS memory and confirms IS stable during warm-up | — | mstr_cache_warmer.py | ≥ 70% of top-50 reports show status = EXECUTED; IS memory stable
2.10 | Phase 2 completion sign-off — ready for validation | HCL PM presents completion checklist; all 2.01–2.09 acceptance criteria met | EBI Coordinator confirms all items checked; signs Phase 2 completion record | Business Sponsor informed of Phase 3 start | — | Signed Phase 2 completion record on file
PHASE 3 — VALIDATION & SIGN-OFF
3.01 | Automated validation — full diff vs on-prem baseline | Run full_validation_runner.py; review DIFF_REPORT.csv output | EBI MSTR Admin reviews output; confirms no unexpected findings | — | full_validation_runner.py | DIFF_REPORT.csv generated; CRITICAL count identified and logged
3.02 | CRITICAL defect remediation | Fix all CRITICAL items; re-run section-specific scripts as needed | EBI ACL Specialist raises any ACL/access items that are blockers | — | REST API + Command Manager | Re-run of full_validation_runner.py shows CRITICAL count = 0
3.03 | HIGH defect remediation | Fix HIGH items; document any accepted risk items for sponsor review | EBI Coordinator logs any accepted risks with mitigation | Business Sponsor approves any accepted HIGH risk items | REST API + Command Manager | All HIGH items either fixed or formally accepted by sponsor
3.04 | Business UAT — priority reports | Provide test environment access; support BA with any technical queries | EBI Change Lead coordinates UAT schedule and tracks sign-off status | BA & Report SMEs test 5–10 priority reports; log results | MSTR Web / Workstation | All priority reports pass; BA sign-off sheet completed
3.05 | Resolve UAT defects | Fix all UAT-blocking defects raised by business | EBI Coordinator prioritises and tracks defect resolution | BA confirms fixed reports pass on re-test | REST API / MSTR Admin | Zero UAT-blocking defects outstanding at go-live gate
3.06 | AI sign-off report + stakeholder review | Feed VALIDATION_REPORT.txt to AI; produce sign-off document | EBI Change Lead distributes sign-off document for review | Business Sponsor reviews and countersigns the sign-off document | Claude / ChatGPT | Countersigned sign-off document on file
3.07 | Final go/no-go gate and CMC cutover | HCL PM presents full evidence package at go/no-go meeting | EBI Coordinator chairs meeting; confirms all gates green | Business Sponsor provides formal approval email/ticket | All validation scripts | Formal approval on record; cutover time confirmed; rollback plan documented
POST-MIGRATION & HYPERCARE (SRE team engages from here)
4.01 | Week 1 hypercare — HCL on-call support | HCL engineers on-call; P1 response ≤ 2 hrs; P2 response ≤ 4 hrs | EBI Coordinator acts as internal triage point; logs all incidents | Business team reports issues via agreed channel | Monitoring + ticketing | No P1 unresolved > 4 hrs in Week 1
4.02 | SRE onboarding — platform setup (GKE, secrets, monitoring) | HCL hands over architecture docs and script inventory | EBI MSTR Admin briefs SRE on MSTR-specific requirements | — | All toolkit scripts | SRE team confirms they can run harvest + validation independently
4.03 | Final handover and project close-out | HCL PM delivers final status report, lessons learned, and all scripts | EBI Coordinator accepts handover; confirms ongoing ownership | Business Sponsor confirms project complete | — | Handover sign-off; HCL engagement formally closed

## Effort Summary
Estimated Effort per Team per Phase (Automated Toolkit — Medium Instance)
Phase / Activity | HCL Hrs | EBI Hrs | Business Hrs | SRE Hrs (Post-Migration) | Calendar Days
PHASE 1 — DISCOVERY
Harvest, AI analysis, user audit | 6–10 | 3–4 | 2–3 | — | 1–2 days
Connectivity test & ACL requests | 2–3 | 2–3 | — | — | 0.5 days
Documentation & Phase 1 gate | 2–3 | 2 | 2 | — | 0.5 days
Phase 1 Subtotal | 10–16 | 7–9 | 4–5 | — | 2–3 days
PHASE 2 — MIGRATION EXECUTION
Package migration (per project) | 3–6 | 2–3 | — | — | 0.5–1 day
User / group / security filter mig. | 1–2 | 1–2 | 1 | — | 0.25 days
DB connections + JDBC fixes | 3–5 | 2–3 | — | — | 0.5–1 day
VLDB, schedules, LDAP, SMTP | 2–3 | 2 | 1 | — | 0.5 days
Cache warm-up + Phase 2 gate | 1–2 | 1–2 | 1 | — | 0.5 days
Phase 2 Subtotal | 10–18 | 8–12 | 3 | — | 3–4 days
PHASE 3 — VALIDATION & SIGN-OFF
Automated diff + CRITICAL fixes | 4–8 | 2–4 | — | — | 1–2 days
HIGH fixes + business UAT | 2–6 | 2–3 | 6–8 | — | 2–3 days
Sign-off report + go/no-go gate | 1–2 | 2–3 | 2–3 | — | 0.5–1 day
Phase 3 Subtotal | 7–16 | 6–10 | 8–11 | — | 3–6 days
POST-MIGRATION & HYPERCARE
Week 1 hypercare (HCL on-call) | 8–16 | 4–6 | 2 | — | 5 days
SRE onboarding & handover | 4–8 | 3–5 | — | 8–16 | 3–5 days
Monitoring, secrets, platform | — | 2 | — | 8–12 | 3 days
Post-Migration Subtotal | 12–24 | 9–13 | 2 | 16–28 | 10–13 days
TOTAL (Medium Instance)
TOTAL ESTIMATED HOURS | 39–74 | 30–44 | 17–21 | 16–28 | 18–26 days
Manual equivalent (no automation) | ~250 | ~80 | ~60 | ~40 | ~42 days
Savings vs. manual (automation) | ~72% | ~55% | ~70% | N/A | ~55%